## Sheet1
Sysnet Ticketing System
Priority | Function List | Remarks | Status | Status Remarks
Master
1 | Company |  | 100% | Completed
1 | Technician |  | 100% | Completed
| Category |  | 100% | Completed
| SubCategory |  | 100% | Completed
1 | SLA |  | 100% | Completed
1 | Customer |  | 100% | Completed
| Vendor |  | 0% | Not yet start
1 | QuickCard | ReStructure | 100% | Completed
QuickCard List
Edit Quickcard Detail
View Quickcard Dtails
| Quickcard Phase |  | 100% | Completed
| Quickcard SLA |  | 100% | Completed
| Quickcard Task |  | 100% | Completed
2 | CMDB - Customer asset/equipment details |  | 0% | Not yet start
| Ticket Status | from API level | 100% | Completed
| TicketType | from API level | 100% | Completed
| Priority | from API level | 100% | Completed
| TicketMode | from API level | 100% | Completed
| PartnerStatus | from API level | 100% | Completed
| EscalationType | from API level | 10% | Completed
| EmployeeType | from API level | 100% | Completed
Dashboard
| Tickets Status and Summary |  | 100% | Completed
Open Tickets
In-Progress
Completed
| Today Schedule |  | 100% | Completed
| Technician Availability |  | 50% | Progress
1 | Transaction - Restructure
| TicketList |  | 100% | Completed
Quickcard Ticket Creation
Ad-hoc Ticket Creation
| TicketDetails |  | 90% | Progress
| Attachments |  | 100% | Completed
Attchments List
Add Attachment
Remove Attachment
| Task |  | 100% | Completed
Task List
Create Task
| Edit Task |  | 100% | Completed
Task cooments
Task Assign
Task Worklog
| Task Attachment |  | 100% | Completed
Add Attachment
Remove Attachment
Task Status
| Schedule |  | 100% | Completed
Schedule List
Create new Schedule
Edit Schedule
| Worklog |  | 100% | Completed
Worklog List
Create Worklog
| Activities |  | 0% | Not yet start
Activites List
| Comments |  | 100% | Completed
Comments List
Add Comments
Edit Comments
| Assign Ticket |  | 100% | Completed
Assignee List
Assign Ticket
| Task List |  | 100% | Completed
All Task list
| Schedules |  | 100% | Completed
Upcoming Schedule list
Schedule list by calender
Report
| Service Report |  | 100% | Completed
| Create Service Report |  | 40% | In Progress
Email Notification
| Ticket Creattion |  | 100%
| Ticket Schedule |  | 100%
| Service Report |  | 0%
Settings
2 | Role Management |  | 30% | In Progress
Function List
R/W/D Access
2 | User Management
| User List |  | 100% | Completed
| Edit User Details |  | 100% | Completed
| User Profile |  | 50%
1 | Mobile APPS - Restructure |  |  | Not yet Impletment
| Framework | Initial Ionic framework | 100%
| Dashboard |  | 100% | Completed
| Today Schedule | No. of Today Schedule
| Today Task | No. of Today Task
| Total Tickets | No. of Total Tickets
| Service Report | No. of service report
Calender
| Tickets |  | 100% | Completed
TicketList
TicketDetail
Add Ticket Attachments
Worklog List
| Ticket Comments |  | 100% | Completed
Add Comments
Edit Comments
Delete Comments
| Task |  | 100% | Completed
TaskList
TaskDetail
Add new task
Add Task attachment
| Schedule |  | 100% | Completed
Shedule list
| ServiceReport |  | 100% | Completed
ServiceReport List
Pending Report List
Create Service Report